# Tazayud Owner PMO — User Manual

Integrated Portfolio & Project Controls System

This manual is for the people who use the platform: what you will see when you sign in, what your role lets you do, and how to do it. It is written for someone who has never used the system, so it explains each step in order. Where a screen refuses something, it says why, and this manual says what that refusal means.

## 1. What this system is

Tazayud is a real-estate developer and owner. Every figure in this system is a cost to Tazayud — money committed to, incurred with, or paid to the consultants and contractors delivering its developments. There is no revenue, margin or profit here; that is deliberate. This is an owner's cost-control system.

### How a development is delivered

Whether a development is run internally or through a Project Management Consultant is a Tazayud policy decision, taken on its value:

| Project value | Delivery route |
| --- | --- |
| 20M or less | Internal, self execution |
| 20M to 50M | PMC if complex, otherwise internal |
| 50M to 70M | PMC considered |
| 70M and above | PMC |

The system records which route was chosen. It does not apply the policy for you: the route is set when the development is registered, and the judgement in the middle two bands is a person's to make.

It holds eight developments across four portfolios:

| Portfolio | Developments |
| --- | --- |
| Residential | RES-01, RES-02 |
| Commercial | COM-01, COM-02 |
| Mixed Use | MXU-01, MXU-02 |
| Land Development | LND-01, LND-02 |

For each development it reports a position: the approved budget, the control budget, what has been committed, incurred, earned, certified and paid, and the anticipated final cost. The position is not typed in. It is built up from reporting periods: each period a project manager files the work-package figures from the PT_TEMPLATE workbook, a second person validates them, a third approves them, and only then does the position move.

Everything is reconciled before it is recorded. Seventeen controls check that the figures agree with each other — that the work packages add up to the control budget, that the cost categories forecast to the adopted final cost, that nothing has been paid that was not certified. A period that fails a control is refused, and the screen tells you which control and by how much.

### The two builds

You may meet the system in two forms:

•  The platform — a website, with a sign-in screen. This is the system of record. Data lives in a database; the workflow, roles and controls all apply. This manual is about the platform.

•  The self-contained demonstration — a single file that opens with a double-click, no sign-in, showing the same screens on sample data. Changes made there stay in that browser and go nowhere. It is a presentation, not a record.

## 2. Signing in

Open the platform address in a browser (Chrome, Edge or Firefox; the current version of any of them). You will see the sign-in screen.

1.  Enter the email address your account was issued with.

2.  Enter your password, exactly as issued. Passwords are case-sensitive.

3.  Press Sign in.

If either is wrong you will see email or password is incorrect. The message is the same whichever was wrong, on purpose. Try again; if you cannot get in, contact the administrator, who can issue a new password. Nobody can look up your existing one — it is not stored, only a one-way hash of it.

Once signed in you will see your name and role at the bottom left, under the navigation. Click it to open My Profile. Your session lasts eight hours, or until you close the browser tab, or until you press the Sign out button beside your name, or on your profile.

Passwords are issued by the administrator and shown to them once. Change yours to something only you know as soon as you have signed in, under My Profile. If you think it has been seen, change it again.

### My Profile

Everything about your own account lives on one screen, reached by clicking your name at the bottom left.

•  Your name. What every screen shows beside anything you file, validate or approve. Change it and the whole system follows immediately.

•  Your picture. Choose an image and it is cropped square and shrunk in your own browser before it is sent, so only a small thumbnail is kept. It appears beside your name. Remove goes back to your initial.

•  Your password. The current one, then the new one twice. At least twelve characters: a phrase you can remember beats a short puzzle you cannot. Your current password is required even though you are already signed in, so a session left open on somebody else's screen is not enough to take your account over.

•  Your role and your developments are shown and cannot be changed here. They are issued to you by the administrator. A screen that let a person set their own role would undo the whole access model with one dropdown.

•  Sign out.

## 3. Finding your way around

The navigation runs down the left. Every module is one click. The list is the same for every role; what you can do in each module depends on your role (section 5).

The scope selector sits at the top of every screen. It decides what the figures on the screen cover:

| Level | Shows |
| --- | --- |
| Corporate | All eight developments rolled up |
| Portfolio | One portfolio's developments rolled up |
| Project | One development |

The Dashboard, Projects, Reports and Analytics screens follow the level you choose. Every other module is about one development — the WBS, the cost position, the registers — so those always show the development named in the Project box, whatever the level says. If you are looking at a register and the figures seem wrong, check which development the selector names.

The scope is part of the page address. A link to the cost position of COM-01 is a link: copy the address bar and send it, and the recipient opens exactly that view.

The shield button at the top right shows the reconciliation state — 20/20 means every control passes for everything in scope. Click it for the full list with both sides of every comparison.

The bell shows how many alerts you have not read. Escape closes any open panel.

## 3b. The assistant, and reading a document

Two things in this system use a language model, and both are deliberately limited. Whether they are switched on depends on the deployment; where they are not, each says so rather than offering a button that fails.

### The PMO assistant

The sparkle button at the top right. Ask about budget, risks, variations or schedule for whatever is in scope.

It cannot do arithmetic, and that is on purpose. Every figure it quotes is computed by this system from the live position and handed to it; it is told that any figure it states must be one of those. Ask something the figures do not cover and it will say so and name the screen that has it, rather than producing a number that looks right.

It also only ever sees the developments you may see. A project manager's assistant cannot answer about a development they are not assigned to.

It changes nothing. Ask it to file, approve or correct something and it will tell you which screen to use.

### Reading a document

AI Extract at the top right, for a project manager, PMO manager or administrator. Drop in a payment certificate as a PDF or a photograph.

What comes back is a form, not an entry. Each field carries how sure the reader was of it:

| Badge | What it means |
| --- | --- |
| Green | Read clearly |
| Amber | Read, but check it |
| Red | Read poorly — check it against the document |
| not read | The reader could not make it out. It has not been guessed |

Correct anything that is wrong, choose the development if it was not identified, then press Create the entry. Only then is anything recorded, and it goes through exactly the same reconciliation controls as a certificate you typed — including the one that refuses to certify more than has actually been spent.

Nothing is filed while you are reading. If you close the window, nothing happened.

## 3a. Messages

Open to every seat, including the executive viewer: the person who may only read the figures is exactly the one most likely to need to ask somebody about them, and a message changes nothing.

The speech-bubble button at the top right, which carries a red count when somebody is waiting for you. It is not in the sidebar: the sidebar lists the things the portfolio is made of, and the badge is what makes a waiting message findable from whichever screen you are on.

Pick a person on the left, type on the right, press Enter to send (Shift+Enter for a new line). The list is ordered by whoever spoke most recently, and shows a count of what you have not read from each person.

Say which development it is about. The dropdown beside the message box attaches a development to what you are saying, and the recipient sees it as a chip they can click to jump straight there. A question about a variation is far easier to answer when the person answering can open the development in one click.

Four things worth knowing:

•  A message never moves a figure. Everything that changes the reported position still goes through Period Entry, Review & Approve, payment claims and the reconciliation controls. Agreeing something here does not file it.

•  Messages are permanent. They are never edited and never deleted, in the same way an account that has acted is withdrawn rather than erased. This is a record, not a chat app — "I told you about that in March" is exactly the sort of claim it exists to settle.

•  Nobody is told when you read something. The unread count is your own; the sender never sees a read receipt.

•  A withdrawn account can still be read, not written to. The conversation stays as part of the record.

New messages appear on their own within about twenty seconds while you have the conversation open, and the count at the top refreshes each minute from anywhere in the application. There is nothing to refresh by hand. If a refresh does not come back, the conversation says so quietly at its foot and keeps trying — nothing you have typed is lost.

## 4. Reading the numbers

Every amount is in Saudi riyals. On tiles, large amounts are shortened: 1.25B is 1,250,000,000; 720M is 720,000,000; 4.9K is 4,900. In tables they are written in full. A minus sign marks a negative.

| Term | Meaning |
| --- | --- |
| Approved Budget (BAC) | What the board has approved for the development |
| Control Budget | The part of the approved budget allocated to work packages; the rest is reserve |
| Planned Value (PV) | The value of work that was scheduled to be done by the data date |
| Earned Value (EV) | The value of work actually done, measured as package budget × percentage complete |
| Actual Cost (AC) | Cost incurred to date |
| Committed | Contracted and awarded to date |
| Certified | Value contractors have certified for payment |
| Paid | What Tazayud has paid |
| Anticipated Final Cost (AFC) | The adopted forecast of the total at completion |
| Budget Variance | Approved budget − AFC. Positive is favourable (under budget); it is shown green. Negative is an overrun, shown red. |
| SPI | Earned ÷ planned. 1.00 is on schedule; below is behind |
| CPI | Earned ÷ actual cost. 1.00 is on cost; below is over |

SPI and CPI are always calculated from the figures on the screen. They are never typed in.

If a term is unfamiliar, the system will tell you. A small gold marker sits beside a term where a screen first uses it — on a tile label or a column heading. Click it for the definition and the formula the system actually uses, and follow Full definition and what it feeds through to the Glossary module, which holds every term in one place along with instructions for using the system.

The four figures people most often confuse are worth stating plainly:

| Figure | The question it answers |
| --- | --- |
| Approved Budget | What were we given permission to spend? A permission. Set at sanction. |
| Control Budget | What may we spend without asking for the contingency? A discipline. |
| Committed Cost | What have we already promised to pay? An obligation — signed, not spent. |
| Anticipated Final Cost | What will this actually cost when it is finished? A prediction, and the only one of the four that moves every period. |

Portfolio and corporate figures are sums of the developments in scope; the portfolio SPI is the sum of earned values divided by the sum of planned values, not an average of the individual indices.

### Reading a chart on this system

Four rules hold on every chart, and they are worth knowing because they are what let you take a figure off a chart and use it.

Every colour is named. A chart drawing more than one line or bar carries a key underneath it. Where a line is dashed in the chart it is dashed in the key too, so the planned-value curve is identifiable without relying on its colour. A chart with one line has no key: the card heading names it.

Every gridline is the number beside it. The scale is chosen so the lines land on round numbers, and a count axis — incidents, people, non-conformances — never offers half of one. If a line sits between two gridlines you can read its value by eye and be right.

A bar is never cut short. Where a chart has a natural reference — 100% of a commitment, an index of 1.00 — a bar that goes past it is drawn past it. A package paid 112% of what was committed to it looks longer than one paid 100%, because it is.

An empty month is not a zero. See below.

### What the trend charts measure, and what they model

Counted from the rows: incidents, non-conformances and inspections. Each of those carries its own date, so the chart counts them off the register and the months shown are the months the register covers. The parts always sum to the total on the tile above.

This is why a trend may cover fewer months than the year. If your incident register begins in July, the chart begins in July. It does not draw January to June as zero, because a month with no record is not a month in which nothing happened — it is a month nobody recorded, and those are different facts. A zero inside the covered period is a real zero and is drawn.

First time right is inspections passed outright over inspections carried out, accumulated from the start of the record. Every point can be reproduced from the inspection log beside it, and the last point is the register's own figure. A scope with no inspections reports nothing rather than 100%.

Modelled from the progress curve: workforce, productivity, risk exposure and equipment utilisation. Nothing in the system dates those month by month, so the shape of how the development got to today is modelled and each card says so. The last point is always the reported position exactly, so a trend and the tile above it can never disagree about where the development stands today. As periods are filed the modelled months are replaced by what was reported.

## 5. Roles — what you can do

Six seats. Yours is shown under your name. It is set by the administrator when your account is issued and cannot be changed from inside the system. The screens show each seat by its job title; the system name is in brackets.

| Seat shown | System name | Can see | Can do |
| --- | --- | --- | --- |
| Project Manager | contributor | Only the developments assigned to you | File reporting periods and record payment certificates, for those developments. |
| PMC | contributor | Only the developments assigned to you, which may be several | Exactly as a project manager. A consultant holding four developments is one account with four assignments. |
| PMO Team Leader | reviewer | Everything | Validate a filed period, or return it with a note. Cannot file one, cannot approve one. |
| PMO Controls Manager | approver | Everything | Approve a validated period into the reported position; approve variations and payment claims; confirm a payment. Proposes changes to a development — registering, amending, deleting, restoring, closing out, reopening, awarding a package — which the Director then authorises. Cannot file a period, cannot validate one. |
| PMO Director / Executive | director | Everything | Authorises a proposed change to a development, or declines it. Files nothing, validates nothing, approves no period. |
| Executive Viewer | reader | Everything, once it is approved | Nothing changes. Approved figures, every report, read-only. |
| Owner Admin | admin | Everything | Everything above, plus issuing accounts and defining seats. Acts without a second person. |

These six are what the system ships with, not a fixed list. A seat is a row in a table the administrator edits, so what each may do can be changed, and a seventh can be added, from the Administration screen — see Seats and capabilities (#seats-and-capabilities). Nothing in this manual requires a developer or a database.

### What a project manager sees

Your developments, and no others. The Projects register lists them, the dashboard and reports roll up those alone, the scope selector offers only the portfolios they sit in, and a link to a development that is not yours opens one that is. This is enforced by the server, not by hiding rows: a development that is not assigned to you is not sent to your browser at all.

The PMO lead, the PMO manager, a Director and the administrator see the whole portfolio.

This manual uses the system names — contributor, reviewer, approver, reader, administrator — because they say what the role does.

### Separation of duties — the rule that holds whatever your role

The person who enters a period can never validate it or approve it. The person who validates a period can never approve it. The person who proposes a change to a development can never authorise it.

This is enforced in the database itself, not in the screens. If you try, you will see a refusal naming the rule. That refusal is the system working.

One exemption, by the owner's decision: the Owner Admin. That account may enter, validate and approve the same period, so a period can still be reported when the PMO seats are away. It is not silent. The same name then appears at two or three stages of the approval trail on the Review and Approve card, and anybody looking at that period can see that one person carried it through. Every other role is bound exactly as the rule says.

So a period always passes through three different people:

Contributor files it  →  Reviewer validates it  →  Approver approves it  →  it is reported

Until the third step the reported position does not move. A filed or validated period is visible, auditable, and not yet fact.

And a change to what a development IS passes through two:

PMO Controls Manager proposes it  →  Director authorises it  →  it takes effect

Until the second step nothing has moved: the development is not registered, the budget is not amended, the deletion has not happened. See Authorisations (#authorisations).

## 6. Contributor — filing a reporting period

You will do this once each reporting period, for each development assigned to you. Assignments are shown when you sign in; if you try to file for a development that is not yours, the system refuses with not assigned to.

### 6.1 Open the Project Workspace

Click Project Workspace in the navigation. It is one development at a time, so if the scope is set to Corporate or Portfolio it asks which one first: press Open and the top bar then names the development you are in. Every other development is a change of scope in that same top bar.

Across the top is the module tab row — Overview, Monthly Reporting, WBS, Cost, Variations, Procurement, Payment Claims, Manpower, Equipment, Quality, HSE, Risk, Issues, Documents. These are the same screens the sidebar carries; the difference is that here they are one development, and the sidebar rolls them up across a portfolio or the whole company.

Under the tabs is the reporting calendar: a year picker and twelve months, each marked with what the system holds for it.

| The month reads | What it means |
| --- | --- |
| Approved | A period covering it was filed, validated and approved. Its figures are final. |
| Awaiting approval | Filed, and sitting with the reviewer or the approver. |
| Returned | Sent back for correction. It is yours again. |
| Nothing filed | The month is open and nothing has been filed yet. |
| Not reported | Outside the development's programme, or past and never reported. |
| Future | The month has not started. |

The strip shows only what has actually been filed. A month that says Not reported is not a fault in the screen — it is the system saying it holds nothing for that month.

Choose the month you are filing, then open the Monthly Reporting tab. The period number and data date are already filled in from the month you picked, and both stay editable — the period number is yours to state, and the workbook is where it comes from.

The form is PT_TEMPLATE — the workbook you already fill — laid out as a screen, in the same order with the same section numbers:

•  1 & 2 — Development, budget and control budget. Period number, data date, approved budget, control budget, anticipated final cost.

•  4 — Work-package register. One row per package: WBS code, name, budget, planned %, actual %, cost incurred, committed.

•  5 — Cost categories. One row per category: budget, committed, actual, forecast final cost.

Section 3 of the workbook — the earned-value position — is not entered. It is calculated from section 4 as you type, exactly as the workbook calculates it: planned value is budget × planned %, earned value is budget × actual %. The KPI tiles under section 5 show the result.

### 6.2 Start from last period, or from the workbook

The form opens pre-filled from the development's current register — the packages, budgets and percentages as they stand — so you adjust rather than retype.

There are two buttons at the top right of section 1.

Download PT_TEMPLATE gives you the reporting workbook itself, the same sheet this system reads. Take it to site, fill it in, and bring it back. Use this rather than a copy from an old email: the importer refuses a workbook whose rows have moved, and you would only find that out after filling it in.

Import PT_TEMPLATE takes the filled workbook back (.xlsx or .xlsm). The system reads the development's own sheet and fills every field on this screen from it: the period, the data date, the budgets, every work package in section 4 and every cost category in section 5. It does not file anything. Importing is loading, not submitting: look at what was loaded, watch the reconciliation panel, and file it yourself.

If the workbook's structure has been altered — a section moved — the import refuses and names the row rather than reading figures from the wrong place. Download a fresh copy and start again.

### 6.3 Enter or adjust the figures

•  Percentages are entered as whole percentages (0–100).

•  Money is entered in whole riyals; commas are ignored.

•  Add package / Add category add a row. The × at the end of a row removes it.

•  The period number must be a whole number.

### 6.4 Watch the reconciliation panel

Under section 5, three checks update as you type:

| Check | Means |
| --- | --- |
| Work packages break down the control budget | Σ package budgets = control budget |
| Cost categories forecast to the adopted AFC | Σ category forecast = AFC |
| Cost incurred agrees between packages and categories | Σ package cost = Σ category actual |

Each shows both figures and, if they differ, Out by how much. The File button stays disabled until all three reconcile. This is the same check the server makes; the panel exists so the refusal never comes as a surprise.

### 6.5 File

Press File period N for validation. You will see Awaiting validation by a reviewer. Open Review & Approve to see it in the queue with your name on it. You will find no Validate or Approve buttons on your own period — that is the separation-of-duties rule.

If the server refuses the period, the message names the reason: which control failed, or that you are not assigned, or that a validated or approved version of that period already exists. Correct it and file again.

One control is worth knowing in advance: certified within actual cost (control 15). Cost incurred in the period you file cannot be less than what has already been certified for the development — a certificate is evidence of cost incurred, so the position cannot show less. If the refusal names it, the package costs are understated against the certificates already recorded.

### 6.6 If it is returned

A reviewer or approver may return a period with a note saying what to correct. It appears in Review & Approve marked Returned, with their name and the note. Open the Project Workspace, select the month, correct the figures on the Monthly Reporting tab, and file again — the new filing replaces the returned one.

### 6.7 Recording a payment certificate

When a contractor's interim payment certificate (IPC) is certified, record it so the certified and paid figures move:

1.  Open Cost & Financials for the development and choose the Cash Flow tab. The line above the tiles shows what is certified against what is incurred.

2.  Press Record certificate.

3.  Enter the certificate reference (for example IPC-09), the gross certified value, and the retention withheld, in whole riyals.

4.  Press Record certificate in the form.

Certified to date rises by the gross value; payments made rise by the net of retention. Earned value and actual cost do not move — those are reported through the period, not the certificate. A certificate that would take certified value above the cost incurred is refused (control 15): file the period that reports the work first, then the certificate for it. The form tells you how much of the actual cost is not yet certified before you submit.

Every certificate is recorded in the audit log with your name and the time, and appears under History on the development's screens.

### 6.8 Asking for an approved month to be reopened

An approved period is the record of what the owner has spent, so nothing on it can be edited. If a figure in it is wrong:

1.  In the Project Workspace, select the approved month on the calendar.

2.  Press Request to reopen beside the period status.

3.  Say what needs correcting and why. A reason is required — the date and your name are recorded automatically, but why an approved figure had to move is the only part nobody can reconstruct later.

The request goes to the PMO manager as a message. It does not open the form: the figures unlock only if they return the period, and both your request and their decision are recorded. A returned period comes back to you and then passes through validation and approval again — it does not go straight back to approved because it was approved once.

The AI Extract button reads a document only in the self-contained demonstration, where it files a fixed sample certificate. On the platform it says Document extraction is not configured and does nothing, so that an invented certificate can never reach the register. The Cash Flow form is the platform's way to record one.

## 7. Reviewer — validating a period

Click Review & Approve. Each filed period is a card showing the development, period, the earned-value position it implies, and who entered it and when.

On a period marked Awaiting validation you have two buttons:

•  Validate — you have checked the figures and they are right. The period moves to Awaiting approval. It is not yet reported.

•  Return… — something is wrong. Type what needs correcting (the note is required) and press Return with this note. The contributor sees your name and the note.

You will not see an Approve button; approval is a different person's act. You cannot validate a period you entered yourself.

What to check: that the figures match the workbook the project manager sent; that the percentages are plausible against the site position; that cost incurred agrees with the certificates you know of. The reconciliation is already proven — the system would not have accepted the filing otherwise — so your validation is about whether the figures are true, not whether they add up.

## 8. Approver — approving a period

Click Review & Approve. On a period marked Awaiting approval you have:

•  Approve and report — the period becomes part of the reported position. Every screen updates: the development's earned value, actual cost, indices and forecast now reflect it. This is the accountable act, and the audit trail records your name and the moment.

•  Return… — back to the contributor with a note, exactly as a reviewer would.

Before it approves, the system re-runs the reconciliation against the position as it stands now — not as it stood when the period was filed. If something else has moved in between and the period no longer reconciles, it is refused with the controls named. That is rare, and it is right.

You cannot approve a period you entered, or one you validated. You will not see a Validate button.

### Variations

On the Variations screen, opening a variation marked Under Review offers Approve. Approving changes its status and records your name in the audit log; committed cost follows in the next reporting period, because a variation moves no figure until the period that carries it is filed.

### Confirming that a payment was made

Approving a payment claim says what a contractor is owed. It does not say the money has left the account, and on the owner's instruction nothing in this system assumes that it has: paid is confirmed, never inferred, and confirming it is the PMO manager's act alone.

1.  Open Payment Claims for the development and click the claim.

2.  In the panel, press Confirm payment.

3.  Check the amount — it defaults to what is still outstanding on that claim — and enter the value date and the bank or treasury reference.

4.  Press Confirm payment.

Payments made to date rises by the amount transferred. Certified does not move: the work was certified when the claim was approved, and certifying it again here would count the same milestone twice. Earned value and actual cost do not move either — those come from the reporting period.

A transfer that would take payments above what has been certified is refused (control 14), with the amount that is actually available.

Every other seat sees the claim sitting at Approved with a line saying the PMO manager confirms a payment, so a claim that has not yet been transferred never looks like an oversight.

### Releasing retention

A claim paid its full net still holds what was withheld from it as security. At handover and closeout that security is returned, and the door is the same panel: open a Paid claim that still holds retention and the button reads Release retention. The amount defaults to what that claim still holds and is editable; the register applies the release to the oldest claims first, which is what a real release run does. It moves paid and nothing else, and control 14 still bounds it.

### Recording and awarding contract packages

A development buys its work in packages over its whole life, not only on the day it is registered. On Procurement, at development level, Record package does both halves:

1.  A new package — give it a number, a scope, a counterparty and a value. Recorded out to tender it carries an estimate and commits nobody; recorded awarded its value moves committed cost at once.

2.  Awarding a tendered package — pick it at the top of the form. The tender's estimate pre-fills and the award corrects it: the real value, the real counterparty, the award date.

A package that is already awarded cannot be awarded again, and an award that would take committed cost past the approved budget is refused with the figures — before anything is written.

### Registering, amending and retiring a development

Adding a development to the portfolio, correcting its details, and taking one out of it are yours and the administrator's. Nobody else has them, however many developments they hold — a project manager reports on a development; they do not decide what it is called or what its authorised budget is.

See section 10 for how all three work; they are the same screens for you.

### The operational sub-tabs

Four modules carry a second view behind a tab at the top of the screen.

| Module | Tab | What it shows |
| --- | --- | --- |
| Quality | Corrective Actions | What was directed after each non-conformance, who owns it, and whether anybody verified it worked. An action closes only when a verification is recorded — an NCR marked closed with nothing verified means it was filed, not fixed. |
| Risk | Mitigation Plans | What is being done about every risk scoring 8 or above, with the score today and the residual its owner is targeting. A low risk gets no plan: writing one for every entry makes the register paperwork. |
| Manpower | Attendance & Hours | The weeks inside the reporting month. They sum to the manhours the period reports, because they are that figure split rather than a second count of it. |
| Manpower | By Counterparty | The workforce each contractor is actually supplying, with headcount and hours tied to the register. |

| Quality | Inspections | Every inspection carried out, with the non-conformance each failure raised. First time right is the share that passed outright — and because every failure names its non-conformance, the percentage traces back to defects you can open rather than to a figure nobody can follow. |
| --- | --- | --- |
| Quality | Material Approvals | What was submitted before installation and what was decided. A rejected submittal is a delay that has already happened. |
| HSE | Incidents | Every safety event, near misses included. TRIR and LTIFR are computed from these rows and the exposure hours — they are not typed. |
| HSE | Observations | What somebody saw, hazards and good practice alike. |
| HSE | Inspections | Planned HSE inspections and what they found. |
| HSE | Training & Permits | Who must hold each certificate and who does; permits issued this month. |
| Manpower | Resource Plan | The plan against the actual, and the three months ahead. |
| Equipment | Maintenance | What is down, for how long and who has it. No cost — the system holds no equipment rates. |
| Procurement | Tender Pipeline | Packages not yet awarded. They carry an estimate and commit nothing. |

Each of these is derived from the register above it and cannot disagree with it. A corrective action names a non-conformance that exists; a mitigation names a risk that exists; a failed inspection names the NCR it raised. None of them holds a cost — money reaches the position through packages, certificates, claims and the period, and nowhere else.

## 9. Reader — reading the position

Everything approved is open to you; nothing can be changed by you.

Approval is publication. A period that has been filed but not yet approved is not part of the reported position, and its figures are not shown to you. On Review and Approve you will see the card, which development and period it is, who filed it, who has validated it, and what it is waiting for. Where the figures would be, the card says they are withheld until the period is approved. Once it is approved they appear, and every screen moves with them.

That is deliberate. A figure that has not been through validation and approval is somebody's working draft, and reporting from a draft is exactly what this system exists to prevent.

The screens most readers use:

•  Dashboard — the portfolio at a glance: budget, AFC, variance, indices, status counts, the S-curve for the chosen scope, top risks by exposure.

•  Projects — every development in a table. Click a row, or the eye icon, to open its Overview.

•  Cost & Financials — six tabs: summary, by category, monthly cost, forecast (three methods and a weighted composite against the adopted AFC), cash flow, commitments.

•  Reports — the report catalogue. Preview any report at the scope you are in, then take it away:

•  Excel saves a .csv of the same figures — the headline four, then a row per development. Excel, Numbers and LibreOffice all open it directly.

•  PDF opens your browser's print dialogue, where every desktop platform offers Save as PDF. What prints is the report sheet alone; the application around it is hidden.

Both are produced in your browser from what is on screen, so the file cannot disagree with the report it came from, and nothing leaves the machine.

•  Messages — the speech-bubble button; direct conversations with anybody else on the system. See section 3a.

•  Sign out — the last button on the right.

•  AI Extract and the assistant — see section 3b.

•  The shield button — the twenty controls with both sides of every comparison. Export Report (CSV) saves the list as a spreadsheet file from your browser; nothing leaves the machine.

•  The assistant (the sparkle button) — answers questions about budget, risk, variations and schedule for the scope you have chosen. Its answers are computed from the figures on the screens by fixed rules; it is not a language model and cannot file a figure.

•  Review & Approve — you can see every filed period and its state, and who did what to it. You have no buttons on it.

## 10. Administrator

You have every capability above, and you are not exempt from separation of duties.

### Accounts

Administration → Users. You are the only role that sees this; everyone else sees their own account and nothing more.

To issue an account, press Add user. Enter the email address, which becomes their identity and their login, their name, and their role. A password is suggested for you — four words and a number, long enough to be safe and short enough to read down a telephone — or type your own. Press Create account.

The password is shown once, on the screen, immediately after you create the account. It is never shown again, because only a one-way hash of it is kept and nobody, including you, can look it up. Send it to the person over something private and ask them to change it under their own profile.

To change an account, press Manage on its row:

•  Role. Changing it takes effect on that person's very next click. Moving somebody out of Project Manager clears their development assignments, since no other role has any.

•  Developments appear for a Project Manager only. Click a development to give or take it away, then Save developments. They see only what is ticked here. No assignment means no access and nothing to file.

•  Reset password issues a new one and shows it once, exactly as when the account was created. Their old password stops working immediately.

•  Withdraw access stops them signing in and ends any session they have open, on their next click. Everything they filed stays exactly as it was, with their name on it. Restore access puts them back.

•  Remove permanently appears only for an account that has never filed, validated or approved anything. Anything else can only be withdrawn: erasing it would leave the audit trail naming somebody who no longer exists.

Three things the system will not let you do, and states plainly when you try:

| You cannot | Because |
| --- | --- |
| Change your own role | Nobody should be able to grant themselves what they were not issued. Ask another administrator |
| Withdraw or remove your own account | It would lock you out of the system you administer |
| Reset your own password here | Yours goes through My Profile, where the current one is required |

### Project assignment

A Project Manager can file only for developments assigned to them, and can see only those. Absence of an assignment is absence of permission. Set them under Manage on the Users tab.

Every development should have at least one Project Manager assigned, or nobody can report on it. The current split — seven developments to Muhammad, LND-02 to Momin — is a testing assumption for the dummy-data phase, not an allocation of responsibility.

### Adding a development

Available to you and to the PMO manager.

Add Project at the top right. Id in the form RES-03 — three capital letters, a dash, two digits — a name, the portfolio, the delivery route, and the approved budget in whole riyals. The delivery route follows the policy in section 1. The form says what is missing or wrong before it lets you create. A new development registered from these four fields starts with nothing spent, a control budget of 95% of the approved budget, and a single Unallocated work package and cost line carrying the whole of it; its registers stay empty until its first period is filed.

#### From the workbook, which is the better way

A development is more than a name and a budget: it has work packages, and those packages are awarded to contractors. Typing them in one at a time is how a development gets registered with half its scope missing.

1.  Download template in the Add Project dialog. Three sheets: 1 Project, 2 Packages, 3 Contracts.

2.  Fill it in. Keep the header row and the field labels where they are — the importer reads them by position and refuses a workbook whose columns have moved, rather than reading a contractor's name into the award-value column.

3.  Import filled workbook. The dialog fills in from what the sheet said and shows you what it implies: how many packages, the control budget they come to, how many contracts are awarded, and what those commit.

4.  Create Project.

Three things worth knowing before you fill one in:

•  A package row with no budget is ignored, and so is a contract row with no contractor or no award value. The template ships six example package rows and one example contract row so you can see the shape; the ones you do not use are simply not registered. The dialog tells you how many rows it ignored, so the figures you are looking at are always the figures of the rows it kept.

•  Package budgets become the control budget. That is the definition: the control budget is the part of the approved budget that has been broken into packages, and what is left is contingency held centrally.

•  Only awarded contracts reach committed cost. Leave the award date blank while a package is out to tender: it carries an estimate and a place in the forecast, and promises nobody anything.

Importing fills the form; it registers nothing. Nothing is written until you press Create Project, which is deliberate — an import that filed straight into the portfolio would be a way to register a development without looking at it.

### Amending a development

Yours and the PMO manager's, on the Projects screen: the pencil beside a development opens Amend.

This is how placeholder names become the real register. Seven fields:

| Field | What it is |
| --- | --- |
| Project Name | The name the development is known by |
| Portfolio | Residential, Commercial, Mixed Use or Land Development |
| Delivery Route | PMC-Delivered or Self-Execution |
| PMC / Delivering team | Who is managing delivery |
| Approved Budget | The Approved Development Budget, in whole riyals |
| Start | When the programme begins — the reporting calendar is cut against it |
| Planned finish | When it is authorised to finish; the duration follows the pair, and a period reported past this date with work remaining reads Delayed |

Every one of them describes the development. Not one of them measures it: cost incurred, earned value, certified and paid come from reporting periods and payment claims that were entered, validated and approved, and no amendment can reach them. That is not a limitation to work around — it is the reason the figures on the dashboard mean anything.

A reason for the amendment is required, and it is kept with your name in the change log.

Two refusals you may meet:

•  "Cannot go below the control budget." The control budget is the part of the approved budget already broken into work packages. Cutting the approved figure below it would not shrink the packages; it would only make the two disagree. Re-plan the packages first.

•  "Nothing has been changed yet." An amendment that changes nothing is not filed, because a change log full of entries that changed nothing is a change log nobody reads.

Only the amendment is recorded — the fields you left alone are left alone, so correcting a spelling does not restate the budget.

### Closing a development out

Yours and the PMO manager's, on the Projects screen, and it is the act for a development that has been delivered — handed over, final account agreed, finished. It is not the same as archiving, and choosing the right one matters.

Press the tick on the row, give the closeout record — the final account reference, the board's decision, whatever was actually agreed — and confirm. Three things then happen.

•  The figures become final. The development stops accepting periods, certificates, payment claims, variations and amendments. Anyone who tries is refused with the reason, whatever their role, including an administrator. This is what makes the closing figures the record of what was spent rather than simply the last numbers anybody happened to enter.

•  It leaves the portfolio arithmetic. The KPI tiles, the roll-ups and the forecast are about the work still in delivery, so a finished development is no longer counted in them, and is no longer "on track" or "at risk" — it is closed.

•  It stays completely readable. Every screen still shows it. Scope to it and you get its cost tabs, its WBS, its packages, its claims, its documents and its whole audit trail exactly as they were on the day it closed, with a line at the top of every screen saying so. The Completed tab on the Projects screen lists what has been delivered, and totals the approved budget and the final cost of all of it.

Reopen is on the row in the Completed tab, for the cases that happen: a retention release nobody had recorded, a final account reopened, a defect that comes back. It puts the development back into the portfolio and back into the roll-ups, and it starts reporting again. Both the closure and the reopening stay in the change log, so the record shows what happened rather than only where it ended up.

### Deleting a development, and getting it back

Yours and the PMO manager's, on the Projects screen.

Delete takes a development out of the portfolio. It disappears from every dashboard, every report, every roll-up and every control the moment it is authorised. Nothing is lost: its position, its registers and its whole audit trail are kept exactly as they were.

The dialog asks two things, and both are required:

1.  Why. Written into the change log and shown against the development in the Archive.

2.  How many days it is kept. The system will not accept fewer than thirty — that is the floor, and the dialog says so rather than leaving you with a button that refuses in silence. Thirty is the default; 90 days and 1 year are one click; anything up to two years can be typed.

The Archive tab on the Projects screen lists what has been deleted, with the date it went, the reason, and how many days are left. Inside that window, Restore puts it back in one click, with everything it had. The restored development counts in the KPIs and the reconciliation controls again from that moment, and both the deletion and the restoration stay in the change log — the record shows what happened, not only where it ended up.

After the window closes the development can no longer be restored. The row says so, and the Restore button explains itself rather than sitting dead. From then on an administrator may Remove it permanently — the one act in this system with no way back, which is why nobody else has it.

Remove is also offered on a development that was registered and never used, with nothing certified, nothing incurred and no period ever filed: there is nothing to lose and no audit trail to break.

Nothing expires by itself. The retention period is a date, not a timer. Past it the system refuses a restore and offers a permanent removal — which somebody has to press, and which is recorded like every other act. Your data is never deleted while nobody is looking.

Deleted, closed or archived? Closed means it counted and is finished — the record stays in front of everybody, under Completed. Deleted means it should never have counted, and it is kept in the Archive for as long as you said. If the work was built, close it out.

### Authorisations

Registering a development, amending it, deleting it, restoring it, closing it out, reopening it and recording a contract package against it are the acts that decide what a development IS. On the owner's instruction they take two people.

If you are the PMO Controls Manager, every one of those forms asks you for a reason and its button says Send for authorisation rather than Save. When you press it, nothing moves: the change waits in the queue with your name and your reason on it, and the toast tells you so. You can withdraw your own proposal at any time before it is decided.

If you are the Director, the Authorisations module in the sidebar is your queue. Each card carries one line saying what the change would do, the development it concerns, who proposed it, when, and why. You can:

•  Authorise it — the change is applied immediately, through the same twenty reconciliation controls as any other write. If the position has moved since it was proposed and the change would now break one of them, it is refused here and the control that failed is named.

•  Decline it — nothing moves, and your note goes back to the proposer.

A note is required either way. It is the record of the decision, and it is what the person who proposed the change will read.

You never authorise your own proposal. That is refused by the database itself, not just by the screen. The one exemption is the Owner Admin, whose changes take effect directly — the same standing exemption they hold for reporting periods, so one account can run the portfolio when the seats are away.

One development holds one pending proposal at a time. The second would be authorised against a development the first had already moved.

### The Administration screen

Five tabs. Users is where accounts are issued, given a seat, assigned developments, reset and withdrawn. Roles & Permissions is the live seat table and Portfolios & Routes the live portfolio table — both below. Audit Log is every recorded change — periods approved, certificates recorded, variations approved, developments registered — with who and when. System Settings shows the count of recorded changes.

### Portfolios and delivery routes

Under Portfolios & Routes, an administrator sees every portfolio the system holds, the colour each is drawn in, and how many developments are in it.

Add a portfolio takes a name and a colour. It appears immediately — in the scope selector, in the Projects register's tabs, in the Dashboard's charts, on the Add Project form and in the new-development workbook — with no deploy and no reload. Add a delivery route is the same, with a line saying what the route means instead of a colour.

The colour is one choice, not two: a portfolio is drawn in its own colour wherever it appears, so the pill on a table and the segment in a chart are the same key.

Three things the panel will not do:

•  A portfolio a development is in is never removed. The count beside it is what the Remove button refuses on, and the row says so. Move those developments to another portfolio first — amend each one under Projects — and the button comes alive.

•  A portfolio the product defines is never removed. The four the system was built with are named in its own data.

•  A portfolio cannot be RENAMED, and that is the important one. Every development carries its portfolio's name as its own value, so a rename would quietly detach all of them and nothing would look wrong until a roll-up came back empty. Add the right one, move the developments across, and remove the one that is now empty. Three steps, each of them visible.

A development can only be registered into a portfolio and onto a delivery route the system holds. If a workbook names one that does not exist, the import says so by name rather than filing it under the nearest match.

### Seats and capabilities

Under Roles & Permissions, an administrator sees every seat the system holds and the five things a seat can carry:

| Capability | What it means |
| --- | --- |
| Input | Files reporting periods and records certificates, for assigned developments only |
| Validate | Validates a filed period, or returns it. Never its own input |
| Approve | Approves a validated period and a payment claim, and PROPOSES changes to a development |
| Authorise | Authorises a proposed change to a development before it takes effect |
| Administer | Issues accounts, defines seats, and acts without a second person |

Each is a toggle. Changing one takes effect on that person's next click — they do not need to sign out and back in. Add a seat defines a new one: give it a name (lower case, the way it will appear in a web address), a title people will recognise, one line saying what it is for, and its capabilities. It is then offered wherever an account's seat is chosen.

Four things the screen will not let you do, each for a reason:

•  The Owner Admin seat is fixed. Taking Administer off it is the one click that could lock every administrator out of the system.

•  A seat somebody holds cannot be removed. Move those accounts to another seat first — otherwise their next request would find their seat missing.

•  A seat the system defines cannot be removed — those six are named in the code. Their capabilities can still be changed.

•  Exemption from separation of duties is not a toggle. Only the Owner Admin carries it, and granting it to another seat would dissolve the rule this system exists to enforce. Changing that is a deliberate act by a developer, which is the friction it should have.

### Reset

The Reset to shipped data button on System Settings is refused on the platform unless the deployment has been started with reset explicitly allowed (ALLOW_RESET=1), which is only done while the database holds dummy data. On the live data set it is disabled: the change log is the audit trail, not something a button truncates.

## 11. Modules, one by one

| Module | What it shows | Who can change it |
| --- | --- | --- |
| My Profile | Your name, picture, password and sign-out | You |
| Dashboard | Roll-up for the chosen scope | — |
| Project Overview | One development: position, curve, top risks, and a monthly breakdown — planned value, earned value, actual cost, cost in month, SPI and CPI, one column per month, with the data date marked and later months shown as forecast | Follows filed periods |
| Projects | All developments; drill-down to Overview | PMO manager and Admin register one, by hand or by importing the new-development workbook |
| Project Workspace | One development, every module, every month. The module tab row, the reporting calendar, and the PT_TEMPLATE form on its Monthly Reporting tab. Everyone opens it; each module inside it is offered by the same rule the sidebar uses, so Monthly Reporting appears for the project manager and the administrator only | Everyone reads · contributor files |
| Review & Approve | Filed periods and their state. Not shown to a seat with no part in reporting | Reviewer validates, Approver signs off |
| Authorisations | Changes to a development, proposed and waiting. Shown to the seats that propose and the seats that authorise | PMO manager proposes, Director authorises |
| WBS | The work breakdown with budget, PV, EV, AC per package; expand and collapse; search | Follows filed periods |
| Cost & Financials | Summary, categories, commitments, cash flow, forecast, monthly curve | Follows filed periods and certificates |
| Variations | Variation orders; approval | Approver |
| Change Log | Change requests upstream of variations | — |
| Packages & Contracts | Every contract package with the counterparty holding it, its WBS node, award value, commitment, payments and retention rate; and the same rolled up by counterparty | — |
| Payment Claims | Every claim against a milestone: raised, verified by the consultant, approved by Tazayud, paid; the retention withheld, released and still held as security; and the same by counterparty | Approver, Admin record a claim |
| Evaluation | Each contractor, supplier and consultant scored out of 80 on data the system holds — variations, schedule, claim accuracy, turnaround and quality — with 20 marks reserved for PMO judgement. Reviewer, approver and administrator only | — |
| Manpower | Workforce by trade: headcount, manhours, productivity index. No rates and no labour cost, by design | — |
| Equipment | Plant and utilisation percentages. No hire rates, by design | — |
| Quality | Non-conformances, corrective actions, the inspection log and material approvals, with every count taken from the register. First time right is passed-outright over carried-out, traceable to the named inspections behind it | — |
| HSE | Incidents, observations, HSE inspections, training and permits. Exposure hours come from the workforce register; TRIR and LTIFR are computed from the incident register against those hours, per 200,000 hours, so two developments of different sizes report different rates | — |
| Risk | Register with exposure (EMV); the matrix and category breakdown are counted from it | — |
| Issues | Live issues | — |
| Messages | Reached from the top bar, not the sidebar. Direct conversations with anyone on the system; a message may name the development it is about | — |
| Reports | The catalogue; preview, then Excel (CSV) or PDF via the print dialogue | — |
| Analytics | Indices and forecast comparison | — |
| Documents | Every document referenced on a variation or non-conformance in scope. References only: no file store is connected, and Open, Download and Upload say so | — |
| Glossary | Every term with the formula the code computes, the six steps of the reporting cycle, and a link to this manual | — |
| Administration | Your account, the roles, the audit log | — |

Every register has a filter bar: choose a status or category, or type in the search box; Clear resets. Click a row to open its detail panel; the History tab shows the recorded changes for that development, taken from the audit log.

## 12. Messages you may see, and what they mean

| Message | Meaning | What to do |
| --- | --- | --- |
| email or password is incorrect | Sign-in refused | Retype; ask the administrator for a new password |
| this account is no longer active | Your account was removed or changed while you were signed in | Sign in again; contact the administrator |
| role X may not … | Your role does not include that act | Nothing — it is not yours to do |
| … is not assigned to … | The development is not assigned to you | Ask the administrator to assign it |
| the person who entered a period cannot validate it (or approve, or return) | Separation of duties | A different person must do it |
| the person who validated a period cannot also approve it | Separation of duties | A different person must approve |
| would break N of 17 reconciliation controls: … | The figures do not agree with each other | Correct them; the controls are named |
| Out by 1,234,567 on the entry screen | Two sides of a check differ | Adjust until they match |
| period N … has already been validated or approved; it cannot be replaced | You are re-filing a period that has moved on | Ask a reviewer to return it first |
| a return needs a note saying why | You pressed Return with no note | Type the reason |
| the request body is too large | An upload over the limit | Use the unmodified template |
| the current password is incorrect | Changing your password needs the one you have now | Retype it; ask the administrator to reset it if you have forgotten |
| a password must be at least 12 characters | Too short | Use a phrase rather than a word |
| … already has an account | That email address is already issued | Manage the existing account instead of issuing a second |
| … has filed or approved work and cannot be erased | Their name is in the audit trail | Withdraw the account instead; it keeps the history |
| you cannot change your own role | Nobody grants themselves a role | Ask another administrator |
| only a project manager holds development assignments | You tried to assign a development to another role | Change the role first, or assign it to a Project Manager |
| Document extraction is not configured | No model is connected on this deployment | Enter the period on the workspace's Monthly Reporting tab; record certificates on the Cash Flow tab |
| no such development on a link you were sent | It is not assigned to you | Ask the administrator to assign it, or ask a colleague who holds it |
| … has reported figures and can only be archived, not removed | You tried to erase a development that has reported something | Archive it instead; its history has to survive |
| … was closed out on … and no longer accepts figures | The development has been closed out; its figures are final | If it genuinely still has something to record, reopen it from the Completed tab first |
| role … may not see archived developments | Only the PMO manager and the administrator can | Ask one of them |
| The figures in this period are not shown because it has not been approved | You are a Director and the period is still in the workflow | Wait for approval; approval is what publishes figures |
| Exceeds cost incurred: only N SAR of actual cost is not yet certified | The certificate is larger than the uncertified cost | File the period that reports the work first |
| No document store is connected in this release | Documents are listed by reference only | Keep the file where it is held today |

## 13. Getting help

The ? button at the top right opens this manual. For an account, a password or an assignment, contact the administrator. For a figure that looks wrong, open the shield button: if a control is failing it will say which, and the History tab on the register shows what changed and who changed it.